## Fabric pipline and stock
SN | Bulk fabric Selection Date | Bulk Fabric Swatches images | Bulk Fabric Description(Composition) | Bulk Fabric Width and L | Cost/mtr | Bulk Fabric Testing Date(Shrinkage/lint etc) | Fabric Description | Total Amount | Payment Status | Purchase Qty | balance | Style No
1 | 2017-03-03 |  | 100%poly ggt | width -42"/l-98 | 28 | 2% |  |  | in house |  | finshed | CSRM31707
2 | 2017-03-03 |  | 100%POLY CREPE | width-44"/l-98 | 28 | 3% |  |  | in house |  | finshed | CTOP31712
3 | 2017-03-03 | print | 30"s rayon | 54" | 75 | 2% |  |  | in house | 142.5 | finshed | CTOP31713
4 | 25/2/2017 | print | cotton | width-54"/l-99 | 50 | 2% |  |  | in house | 242
5 | 27/2/2017 |  | 100%poly | width -42"/l-98 | 28 | 2% |  |  | in house |  | finshed | ctop31714
6 | 27/2/2017 |  | 100%poly | width -42"/l-98 | 28 | 2% |  |  | in house |  | finshed | ctop31714
7 | 2017-03-03 |  | 100%poly | width-44"/l-98 | 45 | 2% |  |  | in house | 90.5 | finshed | CSRM31707
8 | 2017-03-03 |  | 100%poplin | width-54"/l-99 | 50 | 2% |  |  | in house | 100
9 | 2017-09-03 |  | 100%cotton gauze | width-44"/l-98 | 50 | 2% |  |  | in house |  | finshed | CSRM31707
10 | 27/2/2017 |  | 100%poly | width-44"/l-98 |  | 2% |  |  | in house
11 | 2017-03-03 |  | 100%rayon | width-44"/l-98 | 60 | 2% |  |  | in house | 99 | finshed | CSRM31707
12 | 27/2/2017 |  | 100%rayon | width-44"/l-98 | 60 | 2% |  |  | in house | 100 | finshed | CSRM31707
13 | 27/2/2017 |  | twill | width -54"/L-98 |  | 2% |  |  | in house
14 | 15/3/2017 |  | rayon | width-54"/l-99 | 50 | 2% |  |  | in house |  | finshed | csrm31709
15 | 15/3/2017 |  | 100%cotton | width-44"/l-98 | 50 | 2 |  |  | in house |  | finshed | csrm31708
16 | 20/3/2017 |  | 100%cotton | width-44"/l-98 |  |  |  |  | in house |  | finshed | csrm31706
17 | 22/3/2017 |  | 100%viscose | w-54 | 55 | 2%` |  |  | in house | 100 | finshed | csrm31709
18 | 2017-02-03 |  | 100%viscose | 98 | 52 | 2% |  |  | in house |  | finshed | csrm31706
19 | 22/3/2017 |  | 100%poly | [5 empty] | in house |  |  | ctop31712
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
Note on H1: Add Fabric Description -Yogesh Mishra

## Final T&A
SN | Brands | style Code | Image | status | Variation | Variation Details |  | Fabric In Date | Trims In Date | Master pattern date | Sampling Date | Pattern Grading Date | PP sample sumbit date | pp sample lock date | cutting Start Date | cutting end date | emb start | emb end | sewing Start date | mid line inspection | sewing end date | finsing startdate | finshing end date | final inspection date | stock-in warehouse | Remarks
1 | Curvy Q | cSRM31706 |  | Planned | Fabric | rayon | Blue Strip | 2017-02-25 | 2017-03-05 | 2017-03-06 | 2017-03-07 | 2017-03-08
|  |  |  | Actual | Fabric | rayon | in house white and blue |  |  | 2017-07-03 | 2017-08-03 | 2017-09-03 | 9/3/2017 check and ok for producation |  | 2017-10-03 | 2017-10-03 | no | no | 2017-11-03 | 15/3/2017 | 17/3/2017 | 16/3/2017 | 17/3/2017 | 18/3/2017 | 18/3/2017
[6 empty] | 100%cotton | akrm (gray) | 22/3/2017
Note on B1: Write Brands Name If WE mfg same style in different brand then write other brand name -Yogesh Mishra
Note on F1: Variation means Style have color variation or fabric variation -Yogesh Mishra
Note on G1: If Color Varation write color name like red green blue etc better if you write exact code. if fabric variation write cotton denim etc -Yogesh Mishra
Note on H10: not buy yet -Yogesh Mishra

## ATS
Do DATED 16.2.15
S.NO | INTERNAL IDENTIFIER | IMAGE | STYLE NO. | OPTION CODE | CATEGORY | DEFAULT TAG | COLOUR | FABRIC | FIT | SLEEVE LENGTH | PRODUCT DESCRIPTION | QTY | CONSUMPTION |  | Garment qty | XS | S | M | L | XXL | XXL | Fabric unit price | Fabric cost | Trim cost | RAPL COST | TARGET CMP | FOB | MRP | Delivery date
1 | ctop31713 |  | ctop31713 | ctop31713 | WOMENS WEAR shirt | WOMENS WEAR shirt | stripe print | rayon | FITTED | full | eyelet ,stopper and button used |  | 1.2 |  | 50 | 5 | 12 | 12 | 8 | 8 | 5 | 48 | 132 | 14 |  | 120 | 252 | 799
2 | KB DEC PANTS 01 |  | 11763000701 | 11596600701 | WOMENS WEAR PANTS | W0MENS WEAR WOVEN PANTS | BLACK | COTTON STRETCH TWILL | FITTED | NA | DOUBLE BUTTONED FITTED FORMAL PANTS |  | 1.3 |  | 154 | 16 | 36 | 36 | 25 | 25 | 16 | 150 | 195 |  |  | 120 | 315 | 799
3 | COLOUR BLOCK SKIRT |  | 11763107901 | 10802200701 & 10802707901 | WOMENS WEAR SKIRT | W0MENS WEAR WOVEN SKIRT | BLACK/WHITE | COTTON STRETCH TWILL | FITTED | NA | SIDE ZIP NEGATIVE POSITIVE COLOUR BLOCK KNEE LENGTH SKIRT |  | 0.65 (Black) | 0.12(white) | 50 | 5 | 12 | 12 | 8 | 8 | 5 | 95,95 | 73.15 |  |  | 100 | 173.15 | 499
4 | KB CONTRAST WAISTBAND SKIRT |  | 11763200701 | 10972903001 & 10883003001 | WOMENS WEAR SKIRT | W0MENS WEAR WOVEN SKIRT | BLACK | COTTON STRETCH TWILL | FITTED | NA | KNEE LENGHTH FORMAL SKIRT WITH CONTRAST WAISTBAND AND POCKET. |  | 0.6 | 0.25 | 50 | 5 | 12 | 12 | 8 | 8 | 5 | 150, 145 | 126.25 |  |  | 100 | 226.25 | 499

## Cost summary
s.no | Interal style no. | GARMENT STYLE NO | intake | FOB COST | GOOD IN HOUSE
1 | C-101 | ctop11704nbl | feb
2 | C-101 | ctop11704nbl | feb
3 | C-101 | ctop11704nbl | feb
4 | C-102 | ckft11701nbl | feb
5 | C-102 | ckft11701nbl | feb
6 | C-102 | ckft11701nbl | feb
7 | C-103 | ctop11701blk | feb | 150
8 | C-103 | ctop11701wblu | feb | 150
9 | C-103 | ctop11701blu | feb | 140
10 | C-104 | csrm11705ylw | feb | 160
11 | C-104 | csrm11705brnp | feb | 160
12 | C-104 | csrm11705gry | feb | 160
13 | C-104 | csrm11705brn | feb | 160
14 | C-106 | ctop11705blk | feb | 156
15 | c-106 | ctop11705blk | feb | 169
16 | c-106 | ctop11705blk | feb | 169
17 | C-109 | ctop11702wsl | feb | 153
18 | C-110 | ctop11703wcap | feb | 165
19 | C-111 | csrm11704bmult | feb | 190
20 | C-112 | ctop11706wfp | feb | 132
21 | C-112 | ctop11706bfp | feb | 112
22 | C-113 | ctop11707blk | feb | 187
23 | c-113 | ctop11707red | feb | 187
24 | c-113 | ctop11707navy | feb | 188
25 | c-113 | ctop11707voilt | feb | 188
26 | C-115 | ctop11708wflwr | feb | 125
27 | c-115 | ctop11708wflwr | feb | 125
28 | c-115 | ctop11708wflwr | feb | 125
29 | C-115 | ctop11708wflwr | feb | 125
30 | C-117 | ctop11709nblstr | feb | 103
feb

## T&A
| Brands | style | Image | status | Fabric Inhouse Date and fabric no. | Production Materials In Date | style in date | place order | fit date | PP sample sumbit date | pp sample lock date | pattern grading date | shipment handover | cutting date | sewing start date | sewing end date | finsing startdate | finshing end date | final inspection date | stock-in warehouse | Remarks
1 | Curvy Q | ctop31710 |  | Planned | Pattern and fitting is ok but hold by mishar sir |  | 2017-05-02 |  | 2017-10-02 | 14/3/2017 | 16/3/2017 | 18/3/2017 | 25/3/2017 | 19/3/2017 | 19/3/2017 | 21/3/2017 | 21/3/2017 | 22/3/2017 | 22/3/2017 | 24/3/2017
|  |  |  | Actual |  |  | 2017-05-02
2 | Curvy Q | ctop31711 |  | Planned | we have to buy fabric |  | 2017-05-02 |  | 2017-10-02 | 14/3/2017 | 16/3/2017 | 18/3/2017 | 25/3/2017 | 19/3/2017 | 19/3/2017 | 21/3/2017 | 21/3/2017 | 22/3/2017 | 22/3/2017 | 24/3/2017
|  |  |  | Actual |  |  | 2017-05-02 |  | 2017-10-02 | 14/3/2017 | 16/3/2017 | 18/3/2017
3 | Curvy Q | ctop31712 |  | Planned |  |  | 2017-05-02 |  | 15/2/2017 | 14/3/2017 | 16/3/2017 | 17/3/2017 | 23/3/2017 | 18/3/2017 | 19/3/2017 | 22/3/2017 | 22/3/2017 | 24/3/2017 | 24/3/2017 | 24/3/2017
|  |  |  | Actual |  |  | 2017-05-02 |  |  | 15/3/2017 | 17/3/2017 | 18/3/2017 | 24/3/2017 | 19/3/2017 | 20/3/2017 | 22/3/2017 | 22/3/2017 | 24/3/2017 | 24/3/2017 | 25/3/2017
4 | curvy Q | CSRM31706 |  | Planned |  |  | 2017-05-02 |  | 27/2/2017 | 2017-08-03 | 16/3/2017 | 16/3/2017 | 25/3/2017 | 19/3/2017 | 20/3/2017 | 23/3/2017 | 23/3/2017 | 24/3/2017 | 24/3/2017 | 24/3/2017
|  |  |  | Actual |  |  | 2017-05-02 |  | 27/2/2017 | 2017-08-03 | 16/3/2017 | 16/3/2017 | 25/3/2017 | 19/3/2017 | 19/3/2017 | 23/3/2017 | 23/3/2017 | 24/3/2017 | 24/3/2017 | 24/3/2017
5 |  | cSRM31714 |  | Planned |  |  | 2017-05-02 |  | 15/2/2017 | 15/3/2017 | 16/3/2017 | 19/3/2017 | 26/3/2017 | 20/3/2017 | 21/3/2017 | 22/3/2017 | 22/3/2017 | 24/3/2017 | 24/3/2017 | 24/3/2017
|  |  |  | Actual |  |  | 2017-05-02
6 |  | ctop31714 |  | Planned |  |  | 2017-05-02 |  | 27/2/2017 | 2017-10-03 | 14/3/2017 | 15/3/2017 | 22/3/2017 | 16/3/2017 | 17/3/2017 | 19/3/2017 | 19/3/2017 | 21/3/2017 | 21/3/2017 | 24/3/2017
|  |  |  | Actual |  |  | 2017-05-02
7 |  | ctop31715 |  | Planned |  |  | 2017-05-02 |  | 28/2/2017 | 2017-08-03 | 14/3/2017 | 16/3/2017 | 25/3/2017 | 17/3/2017 | 18/3/2017 | 20/3/2017 | 20/3/2017 | 22/3/2017 | 22/3/2017 | 24/3/2017
|  |  |  | Actual |  |  | 2017-05-02
8 |  | ctop31716 |  | Planned |  |  | 2017-05-02 |  | 28/2/2017 | 2017-08-03 | 14/3/2017 | 17/3/2017 | 25/3/2017 | 19/3/2017 | 20/3/2017 | 22/3/2017 | 22/3/2017 | 24/3/2017 | 24/3/2017 | 24/3/2017
|  |  |  | Actual |  |  | 2017-05-02
9 |  | Tsrm31701 |  | Planned |  |  | 2017-05-02 |  | 2017-10-02 | 14/3/2017 | 16/3/2017 | 18/3/2017 | 25/3/2017 | 19/3/2017 | 19/3/2017 | 21/3/2017 | 21/3/2017 | 22/3/2017 | 22/3/2017 | 24/3/2017
|  |  |  | Actual |  |  |  |  | 14/3/2017 | 17/3/2017 | 17/3/2017 | 18/3/2017 | 26/3/2017 | 20/3/2017 | 21/3/2017 | 24/3/2017 | 23/3/2017 | 25/3/2017 | 26/3/2017 | 26/3/2017
10 |  | TSRM31702 |  | Planned |  |  | 2017-05-02 |  | 2017-10-02 | 14/3/2017 | 16/3/2017 | 18/3/2017 | 25/3/2017 | 19/3/2017 | 19/3/2017 | 21/3/2017 | 21/3/2017 | 22/3/2017 | 22/3/2017 | 24/3/2017
|  |  |  | Actual |  |  |  |  | 14/3/2017 | 17/3/2017 | 17/3/2017 | 18/3/2017 | 26/3/2017 | 20/3/2017 | 21/3/2017 | 24/3/2017 | 23/3/2017 | 25/3/2017 | 26/3/2017 | 26/3/2017
Note on F2: Fabric Use Write -Yogesh Mishra